## Draft Schedule
Below table is draft schedule , and brief work package.
The detail will be added or adjusted later , probably.
| no. | item |  |  | purpose / study target | Date start | Date end | draft schedule
| 00 | Kick off |  |  | understand study schedule and task as a whole | 2020-03-12 |  | Mar12 13:00 - 18:00
| 01 | Establish team environment |  |  | make environment for sharing source and other document | 2020-03-13 |  | Mar13 13:00 - 18:00
git server
aws access
| 02 | Establish client environment |  |  | make environment for maintenance pc | 2020-03-13 |  | Mar13 13:00 - 18:00
ssh , vmware , sourcetree , etc
| 03 | Infrastructure (briefly) |  |  | understand system structure briefly for making clear whole image | 2020-03-16 |  | Mar16 13:00 - 14:00
| 04 | Study , for Debug , Coding |  |  | understand Odoo's basic coding , and how to debug (with Odoo's developer book) | 2020-03-16 | 2020-03-31
|  |  | (1) how to debug |  |  |  |  | Mar16 15:00 -17:00
|  |  | (2)frame work (Odoo) |  |  |  |  | Mar17 13:00-15:00
|  |  | (3)basic design , folder and file structure , access right |  |  |  |  | Mar17 15:30-17:00
|  |  | (4)basic design2 , model , view , inheritance |  |  |  |  | Mar18 13:00-17:00
|  |  | (5)sample coding |  |  |  |  | Mar19 - Mar25 (self study)
(6)sample coding with acutal source
| 05 | Other coding |  |  | understand how to use excel report (user side programing)
|  |  | (1)excel report |  |  |  |  | Mar26 13:00-15:00
|  |  | (2)sample coding by excel report |  |  |  |  | Mar30-31 (self study)
| 06 | webcoop feature |  |  | understand webcoop feature | 2020-04-01 | 2020-04-02
[5 empty] | self study | 2020-04-06 | 2020-04-10
| 07. | Infra structure detail |  |  | understand AWS's production site configuration and folder structure. (for deital can know directly check AWS's server configuration in detail )
|  |  | (1)AWS environment (Production site) |  |  | 2020-04-13 |  | Apr6 13:00-17:00
app , file server, vpn , load balancer , db
|  |  | (2)Create AWS test environment |  |  | 2020-04-14 | 2020-04-17
| 08 | Maintenance |  |  | understand necessary knowledge for server maintenance
|  |  | (1)log , log backup and rotation |  |  | 2020-04-20 |  | Apr20 13:00-14:00
|  |  | (2)backup , backup and rotation , restore |  |  | 2020-04-20 |  | Apr20 13:00-14:00
|  |  | (3)auto shutdown , auto open |  |  | 2020-04-20 |  | Apr20 15:00-17:00
|  |  | (4)vpn key maintenance |  |  | 2020-04-21 |  | Apr21 13:00-14:00
|  |  | (5)create new user's env |  |  | 2020-04-21 |  | Apr21 14:30-17:00
vpn key , create subdomain
|  |  | (6)how to release program |  |  | 2020-04-22 |  | Apr22 13:00-17:00
| 09 | Data migration |  |  | understand necessary knowledge and technic for data migration
|  |  | (1) how to do by import module (easy understandable , but it has limitation) |  |  | 2020-04-27
|  |  | (2) how to do with xml-rpc (more flexible , but need coding technic and need understanding well about odoo ) |  |  | 2020-04-28 | 2020-04-30
10.Other
(1)refer db directly
| 11.Reserved |  |  |  |  | 2020-05-01 | 2020-05-30