## Draft Schedule
Below table is draft schedule , and brief work package.
The detail will be added or adjusted later , probably.
| no. | item |  |  | purpose / study target | Date start | Date end | draft schedule
| 00 | Kick off |  |  | understand study schedule and task as a whole
| 01 | Establish team environment |  |  | make environment for sharing source and other document
git server
aws access
| 02 | Establish client environment |  |  | make environment for maintenance pc | September 23-25
ssh , vmware , etc
| 03 | Infrastructure (briefly) |  |  | understand system structure briefly for making clear whole image | September 28-29
| 04 | Study , for Debug , Coding |  |  | understand Odoo's basic coding , and how to debug (with Odoo's developer book) | September 30 - Oct 16
(1) how to debug
(2)frame work (Odoo)
(3)basic design , folder and file structure , access right
(4)basic design2 , model , view , inheritance
(5)sample coding ( self Practice)
| 05 | Other coding |  |  | understand how to use excel report (user side programing) | October 19-20
(1)excel report
(2)sample coding by excel report
| 06 | Webcoop feature |  |  | understand webcoop feature | October 21- November 6
Self study
| 07. | Infra structure detail |  |  | understand AWS's production site configuration and folder structure. (for deital can know directly check AWS's server configuration in detail ) | November 7 -8
(1)AWS environment (Production site)
app , file server, vpn , load balancer , db
(2)Create AWS test environment
| 08 | Maintenance |  |  | understand necessary knowledge for server maintenance | November 9-10
(1)log , log backup and rotation
(2)backup , backup and rotation , restore
(3)auto shutdown , auto open
(4)vpn key maintenance
(5)create new user's env
vpn key , create subdomain
(6)how to release program
| 09 | Data migration |  |  | understand necessary knowledge and technic for data migration | November 11-13
(1) how to do by import module (easy understandable , but it has limitation)
(2) how to do with xml-rpc (more flexible , but need coding technic and need understanding well about odoo )
10.Other
(1)refer db directly
11.Reserved